## Action log status
STATUS | ACTION ITEM # |  | ASSIGNED TO | DUE DATE | PRIORITY | CLOSED / NOTES
Complete | #1 | Set up MSIFS email for Stephen | Alex | 2026-03-02 | High
Complete | #2 | Send Brent crude analysis and Feb 22 meeting notes to Stephen | Alex | 2026-03-02 | High
Complete | #3 | Send financial model and project finance resource link to all | Alex | 2026-03-02 | High
On Hold | #4 | Continue building out MSIFS website / digital footprint | Alex | 2026-03-08 | High | Limited time prior week (Mar 7 week)
In Progress | #5 | Continue developing fund thesis document | Alex | 2026-03-08 | Medium | needs team review | PRIORITY |  | STATUS
On Hold | #6 | Reach out to Alanna Pope at DFC | Alex | 2026-03-03 | Medium |  | 3-4 weeks | Low | Not Started
In Progress | #7 | Follow up with Lexi Novitske for full-length call | Alex | 2026-03-08 | Medium |  | 1-2 weeks | Medium | In Progress
| #8 | Secure meeting with Afzal (mining/exploration/fundraising advisor) | Hassan | 2026-03-08 | High |  | <1 week | High | Complete
| #9 | Write letter to Kenya Minister of Foreign Affairs re: MSIFS investment commitment, CC Kenya Invest director | Hassan | 2026-03-02 | High |  |  |  | On Hold
| #10 | Begin inroads with official channels to champion MSIFS in East Africa | Hassan | 2026-03-08 | High |  |  |  | Overdue
| #11 | Request financial documents / capital requirements from Ali for EAGOL deal | Hassan | 2026-03-08 | Medium
| #12 | Set up Notion workspace + Slack/communication channels for team | Hassan | 2026-03-08 | Medium
| #13 | Onboard Aibek on Notion (1:1 call) | Hassan | 2026-03-08 | Medium
In Progress | #14 | Continue sourcing and evaluating Kazakhstan projects via gold mining contact | Aibek | Ongoing | High
In Progress | #15 | Evaluate and prioritize project leads — identify which have real substance | Aibek | 2026-03-08 | High
In Progress | #16 | Sound out potential advisory board candidates (assess energy level and interest without revealing full strategy) | Aibek | 2026-03-15 | Medium
In Progress | #17 | Create shared action log (Excel) for tracking tasks, priorities, and history | Aibek | 2026-03-08 | Medium
Complete | #18 | Share Kazakhstan geological conference details with Stephen | Aibek | 2026-04-02 | Low | Extra info: The main areas of the forum's activities: The International Geological Forum GEOSCIENCE & EXPLORATION CENTRAL ASIA brings together specialists in geological exploration, subsoil use, and mineral resources. The forum aims to develop international cooperation and exchange experiences in the use of digital technologies. https://geca-forum.asia/en#rec1769652701
In Progress | #19 | Review financial model and poke holes — flag gaps from capital markets perspective | Stephen | 2026-03-08 | High
| #20 | Review Brent crude analysis; consult with Notre Dame professor on working capital structure for EAGOL deal | Stephen | 2026-03-15 | High
| #21 | Build and filter investor universe list (prioritized) | Stephen | 2026-03-15 | High
| #22 | Reach out to contacts at Morgan Stanley, Moelis, Evercore + project finance teams for market feedback | Stephen | 2026-03-15 | High
| #23 | Collect punchy anecdotes from each team member for one-pager / marketing materials | Stephen | 2026-03-15 | Medium
| #24 | Review financial model and identify gaps from operational experience | All | 2026-03-08 | High
| #25 | Propose potential advisory board candidates within 2 weeks | All | 2026-03-15 | Medium
| #26 | Finish reviewing Partnership document materials | All | 2026-04-01 | High
| # 27 | CERAWeek Conference | Alex | Mar 22-27 | High
| #28 | Fix number mismatches in GP Partnership Agreement; remove numbers from definitions | Alex | 2026-04-01 | High
| #29 | Codify language in Scope doc: regional assignments are flexible/non-exclusive | Alex | 2026-04-01 | Medium
| #30 | Remove placeholder 4th partner from Article 2; remove GP commitment language | Alex | 2026-04-01 | Medium
| #31 | Fix country default risk spread / ERP-by-country reference in financial models | Stephen | 2026-03-29 | High
In Progress | # 28 | Attend CERA Week (Mar 22); send warm outreach to target contacts beforehand | Alex | 2026-03-22 | High
| #32 | Have MSIFS landing page with About Us ready by Wednesday | Alex | 2026-03-19 | High
| #33 | Send Stephen CERA Week target contact list | Alex | 2026-03-19 | Medium
| #34 | Review GP Partnership Agreement and Scope of Responsibility; add comments | Aibek | 2026-04-01 | High
| #35 | Follow up with gold mining contact on Kurzal project — request detailed cost breakdown | Aibek | 2026-03-19 | High
| #36 | Use financial model to test Kurzal project assumptions | Aibek | 2026-03-29 | Medium
| # 29 | Call with Italy/India contact (now in Kazakhstan) re: mining projects and network intel | Aibek | 2026-03-19 | High
| #37 | Continue building Kazakhstan project pipeline via personal network | Aibek | 2026-03-29 | Medium
| #38 | Attend geological conference in Kazakhstan (early April) | Aibek | 2026-04-05 | High
| #39 | Follow-up email to Emanuela Margulu (IFC, World Bank) from D.C. trip | Aibek | 2026-03-22 | Medium
| #40 | Review GP Partnership Agreement and Scope of Responsibility; add comments | Hassan | 2026-04-01 | High
| #41 | Pursue warm introductions ahead of Kenya Investment Conference (Mar 25) via law firm contact | Hassan | 2026-03-25 | High
| # 30 | Reconnect with Absol re: mining/fundraising expertise in Central Asia | Hassan | 2026-04-01 | Medium
| #42 | Attend geological conference in Kazakhstan (early April) | Hassan | 2026-04-05 | High
| #43 | Confirm MSIFS digital footprint readiness with Alex before sending outreach under MSIFS email | Hassan | 2026-03-19 | Medium
| #44 | Review GP Partnership Agreement and Scope of Responsibility; add comments | Stephen | 2026-04-01 | High
| #45 | Finalize one-pager for initial investor outreach | Stephen | 2026-03-29 | High
| #46 | Filter and prioritize investor universe list to top prospects | Stephen | 2026-03-29 | High
| # 31 | Share one-pager with Tortoise Ecofin contact for feedback | Stephen | 2026-03-29 | Medium
| #47 | Review six split financial model verticals | Stephen | 2026-03-29 | Medium
| #48 | Fix country default risk spread / ERP-by-country formula issue in models | Stephen | 2026-03-29 | High
| #49 | Connect with Alex during SERA Week; help with warm intros from Houston network | Stephen | 2026-03-22 | Medium